## Test Plan
Please click here for Meena Bazar testplan full PDF.

## Mind Maps
Mind Map of Meena Bazar Web Application

## TestScenarios
Project Name | MeenaBazar
Reference Document | FRS
Created By | Md. Kawsar Hossain
Creation Date | 28/02/2025
Approval Date
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 |  | Validate login with valid credentials and homepage redirect. | P0 | 15
TS_002 |  | Validate that all user account-related functionalities work as expected | P1 | 33
TS_003 |  | Validate logout and redirect to home page. | P0 | 5
TS_004 |  | Validate that featured products, special offers, and new arrivals are displayed correctly, linked properly, and sorted as expected. | P1 | 27
TS_005 |  | Validate navigation through product categories. | P0 | 15
TS_006 |  | Validate search bar returns accurate results. | P0 | 12
TS_007 |  | Validate adding, updating, and removing cart items. | P0 | 10
TS_008 |  | Validate tracking order status with accurate updates. | P2 | 6
TS_009 |  | Validate that the checkout process works seamlessly | P0 | 30
TS_010 |  | validate that all footer elements work as expected | P2 | 18
TS_011 |  | Validate website compatibility across browsers and devices. | P0 | 1

## TestCase
Product Name |  | MeenaBazar | TC Start Date | 28/02/2025 | TC Execution Start Date | - - | [5 empty] | TEST CASE
Module Name |  |  | TC End Date | 2025-04-04 | TC Execution End Date | - - |  |  |  |  | PASS | 166
Epic |  |  | Test Case Developed By | Md. Kawsar Hossain | Browser (tested) | Yes |  |  |  |  | FAIL | 9
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | No |  |  |  |  | NO RUN | 0
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 175
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 | Account |  | Login | Verifying login OTP is sending or not | Should send an OTP to the provided email address/phone number | Found as per expectation | kawsar@yopmail.com,01732066805 | Step-1: Click on Sign In button Step-2: Provide a valid email/phone to sign in Step-3: Check mail inbox for OTP |  |  | Passed
2 |  |  |  | Verifying Login with valid Email | Should be able to login using valid email | Found as per expectation | kawsar@yopmail.com | Step-1: Click on Sign In button Step-2: Provide an email to sign in Step-3:Recieved an OTP and entered it to login |  |  | Passed
3 |  |  |  | Verifying Login with Invalid OTP | Should give an error message to the user to provide correct OTP | Found as per expectation with error message showing "Please Enter a Valid Pin Code!" | 121441 | Step-1: Click on Sign In button Step-2: Provide a valid email/phone number to sign in Step-3: Input invalid OTP |  |  | Passed
4 |  |  |  | Verifying eye icon is present in the OTP field and is working | Initially the OTP field should be masked and upon clicking the eye icon the OTP field should display the OTP in plain format | Found as per expectation | 121345 | Step-1: Click on Sign In button Step-2: Provide a email to sign in Step-3: Enter digits in OTP field Step-4: Click on eye icon to check |  |  | Passed
5 |  |  |  | Verifying OTP re-send functionality | Should re-send an OTP to the given email/phone | Didn't find as per Expection, showing the message "OTP is send to Your Mobile Number" but now sending the OTP to the email |  | Step-1: Click on Sign In button Step-2: Provide a valid email to sign in Step-3: Wait 2 minute for the re-send button to appear in place of the timer Step-4:Click on Re-Send button Step-5:Check Email for re-sent OTP | Resend_button_error.png |  | Failed
6 |  |  |  | Verifying Login with Invalid Email | Should give an error message to the user to insert valid email address | Found as per expectation with error message showing "Invalid Mobile Number Or Email" | kawsar@gmail | Step-1: Click on Sign In button Step-2: Provide an invalid email to sign in |  |  | Passed
7 |  |  |  | Verifying Login with valid Phone Number | Should be able to login using valid phone number | Found as per expectation | 1732066805 | Step-1: Click on Sign In button Step-2: Provide a valid phone number to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name |  |  | Passed
8 |  |  |  | Verifying users can go back and change their given email/phone in case of input mistake in email/phone field | Should be a back button to revisit the email/phone input field and edit the mail/phone number or should be able to close the sign in button and start from beginning after pressing Sign In button | Not Found as per expectation.After entering the email/phone number and proceeding to the next step, closing the sign-in form and reopening it does not reset the process. Instead, it resumes from the previous state. Additionally, there is no Back button available to navigate to the previous step, preventing users from modifying their entered credentials. |  | Step-1: Click on Sign In button Step-2: Provide a phone/email to sign in Step-3: Close the sign in field and click on sign in button again | Sign_in_reattempts.mp4 |  | Failed
9 |  |  |  | Verifying Cursor is on the email/phone number input field once the Sign in button is clicked | The Cursor should be on the input field after clicking the sign in button | Not Found as per expectation |  | Step-1: Click on Sign In button | cursor_error.jpg |  | Failed
10 |  |  |  | Verifying the user is notified and returned to home page after successful login | The user should be notified about successfull login and returned to the home | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name |  |  | Passed
11 |  |  |  | Verifying if the user stays logged in after refreshing or reopening the site | The user should be logged in unless they log out or session expires | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Close the page or reload the page |  |  | Passed
12 |  |  |  | Verifying user name is stored after first successfull login | The username should be stored against the user phone or email address so that user dont need to enter it everytime they log in | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Log Out and Log in Again with the same number/email |  |  | Passed
13 |  |  |  | Verifying that the login UI has no grammartical or spelling mistakes | Shouldn't be any grammartical or spelling mistakes | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Check for any grammartical or spelling mistakes throughout these above mentioned steps |  |  | Passed
14 |  |  |  | Verifying Sign in button doesn't appear once the user is logged in | The Sign In button shouldn't be displayed once the user is logged in | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Check if the Sign In button appear in any pages |  |  | Passed
15 |  |  |  | Verifying logged in user's protected URL isn't accessible by copying into other browser or from other account | The URL shouldn't be accessible and it should redirect to home page if tried to access | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Go to any user-end page Step-6: Copy the URL into some other browser or other profile and try to access it |  |  | Passed
16 |  |  | Personal Info | Verifying all personal Info field are accessible and modifyable | Should be accessible to the user and can modify all the fields | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My Account Button and go to dashboard Step-6: Go the Personal Info Step-7: Try to access and modify all the fields |  |  | Passed
17 |  |  |  | Verifying the page has no grammertical or spelling mistakes | Shouldn't be any grammartical or spelling mistakes | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My Account Button and go to dashboard Step-6: Go the Personal Info Step-7: Check for mistakes |  |  | Passed
18 |  |  |  | Verifying the email field is checking for valid email | Should be giving error message on invalid email | Found as per expected | kawsar.com,kawsar@gmail.com | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My Account Button and go to dashboard Step-6: Go the Personal Info Step-7: Input invalid email address to check error message |  |  | Passed
19 |  |  |  | Verifying personal infos are getting stored after saving them | Should store the values for all the input fields | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My Account Button and go to dashboard Step-6: Go the Personal Info Step-7: Provide all the info and Click on Update |  |  | Passed
20 |  |  |  | Verifying the fields can be updated with new values/blank | Should be able to update or keep the fields blank | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My Account Button and go to dashboard Step-6: Go the Personal Info Step-7: Provide all the info and Click on Update Step-8: Try to modify some fields or keep some fields blank then click on update |  |  | Passed
21 |  |  |  | Verifying all the fields has necessary placeholders | Should have necessary placeholders | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My Account Button and go to dashboard Step-6: Go the Personal Info Step-7: Check all the placeholders |  |  | Passed
22 |  |  | Wish List | Verifying items/products can be added to wish list | Should be able to add products to wishlist | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My account the Go to dashboard Step-6: Click on wishlist Step-7: Click on Add more Step-8: Look for Wish List add button on the product Card and product details page |  |  | Passed
23 |  |  |  | Verifying adding products to wishlist require login | Should require user to login in order to add to wishlist | Found as per expected |  | Step-1: Stay logged out Step-2: Click on Add to Wishlist on a product |  |  | Passed
24 |  |  |  | Verifying adding products to wishlist increase wishlist items count on the wishlist button | Should keep track of total wishlisted items | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My account the Go to dashboard Step-6: Click on wishlist Step-7: Click on Add more Step-8: Add several products to wishlist |  |  | Passed
25 |  |  |  | Verifying adding to wishlist shows a confirmation message of a product being added to wishlist | Should show a confirmation message after adding product to wishlist | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My account the Go to dashboard Step-6: Click on wishlist Step-7: Click on Add more Step-8: Add products to wishlist |  |  | Passed
26 |  |  |  | Verifying products can be removed from wishlist | Should be able to remove products from wishlist | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My account the Go to dashboard Step-6: Click on wishlist Step-7: Click on Add more Step-8: Add several products to wishlist Step-9: Click on wishlist button Step-10: Click on delete icon of the desired prodiuct to be removed from wishlist |  |  | Passed
27 |  |  |  | Verifying products removal from wishlist shows a confirmation message after removal | Should show a success message after removing from wishlist | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My account the Go to dashboard Step-6: Click on wishlist Step-7: Click on Add more Step-8: Add several products to wishlist Step-9: Click on wishlist button Step-10: Click on delete icon of the desired prodiuct to be removed from wishlist |  |  | Passed
28 |  |  |  | Verifying removing product from wishlist decreases total wishlist items in wishlist | Should decrease the number of total wishlist product | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My account the Go to dashboard Step-6: Click on wishlist Step-7: Click on Add more Step-8: Add several products to wishlist Step-9: Click on wishlist button Step-10: Click on delete icon of the desired prodiuct to be removed from wishlist |  |  | Passed
29 |  |  | DashBoard | Verifying user name is showing on dashboard | Should be showing the user name | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My Account Button and go to dashboard Step-6: Check user name |  |  | Passed
30 |  |  |  | Verifying user image can be updated | Should be able to update user image | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My Account Button and go to dashboard Step-6: Click on user image circle and upload photo |  |  | Passed
31 |  |  |  | Verifying dashboard has no spelling and grammartical mistakes | Shouldn't be any grammartical or spelling mistakes | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My Account Button and go to dashboard Step-6: Check for mistakes |  |  | Passed
32 |  |  |  | Verifying order details are updating on dashboard | Should update on each order placed or cancelled | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Place some order and cancel some orders Step-6: Go to dashboard to check if the information updated |  |  | Passed
33 |  |  | Saved Addresses | Verifying addresses page has no spelling or grammartical mistakes | Shouldn't be any grammartical or spelling mistakes | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My account go to dashboard Step-6: Go to addresses |  |  | Passed
34 |  |  |  | Verifying Add button is loading a modal to enter address information | Should load a modal containing necessary input fields | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My account go to dashboard Step-6: Go to addresses Step-7: Click on Add button |  |  | Passed
35 |  |  |  | Verifying address is adding successfully | Should be able to add address and show the added addresses | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My account go to dashboard Step-6: Go to addresses Step-7: Click on Add button Step-8: Fill out the address information then submit |  |  | Passed
36 |  |  |  | Verifying multiple address can be added | Should be able to add multiple addresses | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My account go to dashboard Step-6: Go to addresses Step-7: Click on Add button Step-8: Fill out the address information then submit Step-9:Add another address |  |  | Passed
37 |  |  |  | Verifying default and active address can be set | Should be able to make any address as default address and set addresses as active or inactive | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My account go to dashboard Step-6: Go to addresses Step-7: Click on Add button Step-8: Fill out the address information then submit Step-9: Click on settings Icon to make a particular address default address |  |  | Passed
38 |  |  |  | Verifying address deletion shows an warning | Should show a warning message to confirm deletion | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My account go to dashboard Step-6: Go to addresses Step-7: Click on Add button Step-8: Fill out the address information then submit Step-9: Click on delete icon |  |  | Passed
39 |  |  |  | Verifying addresses can be deleted | Should be able to delete addresses | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My account go to dashboard Step-6: Go to addresses Step-7: Click on Add button Step-8: Fill out the address information then submit Step-9: Click on delete icon Step-10:Click on yes to delete address |  |  | Passed
40 |  |  |  | Verifying after deletion of an address a confirmation message is shown | Should show a confirmation message after successfull deletion | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My account go to dashboard Step-6: Go to addresses Step-7: Click on Add button Step-8: Fill out the address information then submit Step-9: Click on delete icon Step-10:Click on yes to delete address |  |  | Passed
41 |  |  |  | Verifying address can be edited | Should be able to edit address | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My account go to dashboard Step-6: Go to addresses Step-7: Click on Add button Step-8: Fill out the address information then submit Step-9: Click on edit icon Step-10: Edit address and submit |  |  | Passed
42 |  |  | Order History | Verifying order history page has no spelling or grammartical mistakes | Shouldn't be any grammartical or spelling mistakes | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:5: Click on My account go to My Orders |  |  | Passed
43 |  |  |  | Verifying past/current orders are showing in order history | Should show all previous/current orders | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step-5: Make some Orders Step:6: Click on My account go to My Orders |  |  | Passed
44 |  |  |  | Verifying all order related information are available on the order history page | Should show information (e.g Invoice No, Items, Outlet, Status, Payment Status, payment Method, Service Charge, total, Submitted at, Action) | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step-5: Make some Orders Step:6: Click on My account go to My Orders |  |  | Passed
45 |  |  |  | Verifying Payment Status changes as per Payment Paid/Unpaid | Should show payment Status | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step-5: Make some Orders Step:6: Click on My account go to My Orders |  |  | Passed
46 |  |  |  | Verifying all the actions buttons are working | Should be able to view Order Details, View Invoice, Repayment, Reorder | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step-5: Make some Orders Step:6: Click on My account go to My Orders Step-7: Click on all the action buttons to check if they are working |  |  | Passed
47 |  |  |  | Verifying order invoice can be downloaded | Should be able to download invoice | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step-5: Make some Orders Step:6: Click on My account go to My Orders Step-7: Click on invoice Step-8: Click on Download Invoice |  |  | Passed
48 |  |  |  | Verifying order history page UI with no order placed | Should show message like "No Data"/"No Orders Made" | Found as per expected |  | Step-1: Click on Sign In button Step-2: Provide a valid phone number/email to sign in Step-3:Recieved an OTP and entered it to login Step-4:Enter user name Step:6: Click on My account go to My Orders |  |  | Passed
49 |  |  | Log Out | Verifying log out button is not acessible when the user isn't logged in | Should not be able to access the log out button or even see the log out button | Found as per expected |  | Step-1:Open the MeenaBazar URL Step-2:Check for log out button in user unsigned state |  |  | Passed
50 |  |  |  | Verifying log out button logs user out of the system | Should log out the user | Found as per expected |  | Step-1: Click on My account Step-2:Click on log Out |  |  | Passed
51 |  |  |  | Verifying after logout the user is redirected to the home page | Should redirect user to the home page after log out | Found as per expected |  | Step-1: Click on My account Step-2:Click on log Out |  |  | Passed
52 |  |  |  | Verifying what happens if the user press browser back button after log out | The user is not able to access restricted pages and is redirected to the login page or homepage. | Found as per expected |  | Step-1: Click on My account Step-2:Click on log Out Step-3:Press the browser back button |  |  | Passed
53 |  |  |  | Verifying what happens if the user has multiple tabs open and logs out from one tab | The user should be shown a message to log in again and could be redirected to the home page in other tabs | Found as per expected |  | Step-1: Make multiple tabs once logged in Step-2:Click on log Out Step-3:Open other tabs |  |  | Passed
54 | Home |  | Featured Product | Verifying no grammartical or spelling mistake on featured products | Should be no grammartical or spelling mistakes | Found as per expected |  | Step-1:Go to the home page of the site |  |  | Passed
55 |  |  |  | Verifying all featured sections are having products in the section | Should be displaying some products under each featured section | Found as per expected |  | Step-1:Go to the home page of the site Step-2: Go through all the featured sections |  |  | Passed
56 |  |  |  | Veryfying all the product card having the necessary information on them | Should have product image, product title,product quantity, price and add to cart button | Found as per expected |  | Step-1:Go to the home page of the site Step-2: Go through all the featured sections |  |  | Passed
57 |  |  |  | Verifying clicking on each featured product takes the user to product details page | Should navigate the user to product details page | Found as per expected |  | Step-1:Go to the home page of the site Step-2: Click on a featured product |  |  | Passed
58 |  |  |  | Verifying add to cart button is functional | Should add the specific product to cart upon click | Found as per expected |  | Step-1:Go to the home page of the site Step-2: Click on a featured product's add to cart button |  |  | Passed
59 |  |  |  | Verifying Out of stock product displays Add Wishlist button in place of add to cart button | Should display add wishlist button instead of Add to Cart button | Found as per expected |  | Step-1:Go to the home page of the site Step-2: Find a out of stock product |  |  | Passed
60 |  |  |  | Verifying discounted product has their original price along with the discounted price | Should show the original price as well as the discounted price | Found as per expected |  | Step-1:Go to the home page of the site Step-2: Check a featured product |  |  | Passed
61 |  |  |  | Verifying all featured products carousal is working | Should be controlled by next and previous button | Found as per expected |  | Step-1:Go to the home page of the site Step-2: Check featured product carousal |  |  | Passed
62 |  |  |  | Verifying clicking on See All takes the user to all the product collection of that featured section | Should take the user to all product collection page of the particular section | Found as per expected |  | Step-1:Go to the home page of the site Step-2: Click on See All of a featured section |  |  | Passed
63 |  |  |  | Verifying clicking on featured product banner takes the user to all the product collection of that featured section | Should take the user to all product collection page of the particular section | Found as per expected |  | Step-1:Go to the home page of the site Step-2: Click on featured banner of a featured section |  |  | Passed
64 |  |  |  | Verifying all collections are loaded using infinite loading | Should load all the available product using infinite loading | Found as per expected |  | Step-1:Go to the home page of the site Step-2: Click on featured banner of a featured section Step-3: Keep Scrolling to the end of the page |  |  | Passed
65 |  |  |  | Verifying sub category filter is working if single subcategory is selected | Sould load the items of that particular sub category | Found as per expected |  | Step-1:Go to the home page of the site Step-2: Click on See All of a featured section Step-3: Select a sub category |  |  | Passed
66 |  |  |  | Verifying sub category filter is working if multiple subcategory is selected | Sould load the items of those particular sub category | Found as per expected |  | Step-1:Go to the home page of the site Step-2: Click on See All of a featured section Step-3: Select multiple sub category |  |  | Passed
67 |  |  |  | Verifying brand filter is working if single/multiple brand is selected | Sould load the items of those particular brands | Found as per expected |  | Step-1:Go to the home page of the site Step-2: Click on See All of a featured section Step-3: Select multiple brands |  |  | Passed
68 |  |  |  | Verifying product number of each brand/sub category is showed inside the filter | Should show the specific product count beside each subcategory/brand | Found as per expected |  | Step-1:Go to the home page of the site Step-2: Click on See All of a featured section |  |  | Passed
69 |  |  |  | Verifying filter is working if both brand and sub category is selected together | Sould load the items of those particular brands belonging to those particular sub categories | Found as per expected |  | Step-1:Go to the home page of the site Step-2: Click on See All of a featured section Step-3: Select brand and sub category filters |  |  | Passed
70 |  |  |  | Verifying no product is displayed in case no product available for particular filter | Should show blank div or a mesage | Found as per expected |  | Step-1:Go to the home page of the site Step-2: Click on See All of a featured section Step-3: Select brand and sub category filters |  |  | Passed
71 |  |  |  | Verifying featured product image zoom on mouse hover | Should zoom image on mouse hover | Found as per expected |  | Step-1:Go to the home page of the site Step-2: Hover on a featured product image |  |  | Passed
72 |  |  | Special Offers | Verifying all available speical offers banners are showing | Should show banners of all available special offers | Found as per expected |  | Step-1:Go to the home page of the site |  |  | Passed
73 |  |  |  | Verifying speical offer banners are redirecting to available products under the offer | Should show all the discounted product after clicking on special offer banners | Found as per expected |  | Step-1:Go to the home page of the site Step-2:Click on Special offers banner |  |  | Passed
74 |  |  |  | Verifying deals of the week carousal is working | Should show different products by clicking next and previous button of the carousal | Found as per expected |  | Step-1:Go to the home page of the site Step-2:Click on next and Previous button of deals of the week carousal |  |  | Passed
75 |  |  |  | Verifying deals of the week countdown timer is functional | Should show to remaining time left for the discounted product | Found as per expected |  | Step-1:Go to the home page of the site Step-2:Check deals of the week carousal |  |  | Passed
76 |  |  |  | Verifying special offers with minimum purchase requirement | The minimum purchase requirement is clearly stated in the offer details. | Found as per expected |  | Step-1:Go to the home page of the site Step-2:Check special offers with minimum purchase requiremnts |  |  | Passed
77 |  |  |  | Verifying buy 2 get 1 offer products | The buy 2 get 1 condition should be explicitly mentioned on the product | Found as per expected |  | Step-1:Go to the home page of the site Step-2: Go to Buy2 get 1 |  |  | Passed
78 |  |  |  | Verifying bundle product offer | The bundle deal is clearly stated in the offer details. | Found as per expected |  | Step-1:Go to the home page of the site Step-2: Find a bundled deal |  |  | Passed
79 |  |  | New Arrivals | Verifying new arrivals are marked with new arrival badge | Should have a new arrival badge | Found as per expected |  | Step-1:Go to the home page of the site Step-2: Check on the new arrivals |  |  | Passed
80 |  |  |  | Verifying each new arrivals are clickable and are redirected to collections on click | Should be able to click and should navigate to collections page | Found as per expected |  | Step-1:Go to the home page of the site Step-2:Click on the new arrivals |  |  | Passed
81 | Product Management |  |  | Verifying product categories dropdown is functional | The dropdown should open if the user click on categories | Found as per expected |  | Step-1:Click on categories |  |  | Passed
82 |  |  |  | Verifying all the categories are available under the categories | The categories dropdown should hold all the available categories | Found as per expected |  | Step-1:Click on categories |  |  | Passed
83 |  |  |  | Verifying all categories have the available sub categories | All categories have some sub categories. It should show on hover | Found as per expected |  | Step-1:Click on categories Step-2: Hover on each category |  |  | Passed
84 |  |  |  | Verifying clicking on a particular category takes the user to product collection under that category | Should navigate the user to product of that category | Found as per expected |  | Step-1:Click on categories Step-2: Click on each category |  |  | Passed
85 |  |  |  | Verifying clicking on a particular sub category takes the user to product collection under that category | Should navigate the user to all the products of that sub category | Found as per expected |  | Step-1:Click on categories Step-2: hover on each category Step-3: Click on each sub category |  |  | Passed
86 |  |  |  | Verifying product categories with no product | Should show some kind of message on product being unavailable and should not crash | Although it doesn't crash, proper message can be added for the users |  | Step-1:Click on categories Step-2: hover on Pharmacy Step-3: Click on Otc Medicine |  |  | Passed
87 |  |  |  | Verifying all product categories have product cards displayed if available | Should display all the product in cards | Found as per expected |  | Step-1:Click on categories Step-2: Click on a category |  |  | Passed
88 |  |  |  | Verifying all products that are available has add to cart button | Should display an add to cart button if the product is available | Found as per expected |  | Step-1:Click on categories Step-2: Click on a category Step-3:Check of add to cart button |  |  | Passed
89 |  |  |  | Verifying add to cart button is functional | Should add the product to the cart if the button is clicked | Found as per expected |  | Step-1:Click on categories Step-2: Click on a category Step-3:Add a product to the cart |  |  | Passed
90 |  |  |  | Verifying unavailable product have a wishlist button instead of add to cart button | Should have a wishlist button instead of add to cart button if the product is unavailable | Found as per expected |  | Step-1:Click on categories Step-2: Click on a category Step-3: Check if unavailable product has wishlist button |  |  | Passed
91 |  |  |  | Verifying products can be added to wishlist | Should be able to add unavailable product to wishlist | Found as per expected |  | Step-1:Click on categories Step-2: Click on a category Step-3: Click on wishlist button |  |  | Passed
92 |  |  |  | Verifying success message are shown in case of product being added to cart/wishlist | Should show a success message so that user could be aware of that | Found as per expected |  | Step-1:Click on categories Step-2: Click on a category Step-3: Click on wishlist button Step-4:Click on add to cart button |  |  | Passed
93 |  |  |  | Verifying multiple units of a same product can be added to the cart | Should allow a user to add multiple unit of similar product to the cart | Found as per expected |  | Step-1:Click on categories Step-2: Click on a category Step-3:Click on add to cart button Step-4:Click on plus/minus button to adjust quantity |  |  | Passed
94 |  |  |  | Verifying clicking on each product card takes the user to product details page | Should navigate the user to product details page | Found as per expected |  | Step-1:Click on categories Step-2: Click on a category Step-3:Click on a product card |  |  | Passed
95 |  |  |  | Verifying breadcrumbs for each product categories | Should be able to navigate clicking on the breadcrumbs | Not found as expected. Issues with the breadcrumbs of "Personal Care" and "House Hold" category products |  | Step-1:Click on categories Step-2: Click on a "Personal Care/HouseHold Step-3:Click on a product card Step-4: Click on the breadcrumb 2nd level | breadcrumbs_error.png |  | Failed
96 | Shopping Management |  | Product Search | Verifying search box is available in all the pages | Should be available in all the pages | Found as per expected |  | Step-1: Look for searchbar in all the pages |  |  | Passed
97 |  |  |  | Verifying products can be searched by brand name | Should be able to search product by brand name | Found as per expected | lux,unilever | Step-1: Search using a brand name |  |  | Passed
98 |  |  |  | Verifying products can be searched by name | Should be able to search product by name | Found as per expected | shampoo,lotion | Step-1: Search using a product name |  |  | Passed
99 |  |  |  | Verifying search result for unavailable product | Should show a message showing no products found | Found as per expected | watch | Step-1: Search a unavailable product |  |  | Passed
100 |  |  |  | Verifying search with leading spaces | Should show the products omitting the leading spaces | Found as per expected | [leading_spaces]lotion | Step-1: Search a product with leading spaces |  |  | Passed
101 |  |  |  | Verifying search with empty input | Shouldn't search for products | Found as per expected |  | Step-1:Search with empty input |  |  | Passed
102 |  |  |  | Verifying search with category name | Should display products of searched category | Found as per expected | Personal Care | Step-1:Search Personal Care |  |  | Passed
103 |  |  |  | Verifying search with all uppercase.lowercase letters | Should display searched products | Found as per expected | LOTION,lotion | Step-1:Search with all uppercase/lowercase |  |  | Passed
104 |  |  |  | Verify search with partical keyword | Should display all the products that matches the partical search input | Found as per expected | Chin | Step-1:Search with partical keyword |  |  | Passed
105 |  |  |  | Verifying search with numeric characters | Should show related products | Found as per expected | 2 | Step-1:Search with numeric characters |  |  | Passed
106 |  |  |  | Verifying search results are loading quickly for the users | Should load the data in acceptable time | Found as per expected |  | Step-1:Make numerous searches |  |  | Passed
107 |  |  |  | Verifying search with special characters | Should not show any products and display a message | Not found as per expected.Displaying all the products | #!# | Step-1: Search with special characters | searching_with_special_characters_error.png |  | Failed
108 |  |  | Shopping Cart | Verifying products can be added to cart | Products should be added to cart by pressing add to cart button | Found as per expected |  | Step-1: Click on Add to Cart button |  |  | Passed
109 |  |  |  | Verifying multiple products can be added to cart | Multiple Products should be added to cart by pressing add to cart button | Found as per expected |  | Step-1: Click on Add to Cart button of multiple product |  |  | Passed
110 |  |  |  | Verifying floating cart button turns yellow when product a product is added to cart | The cart button should initially be green if no items in cart but should turn yellow if some item is added to cart | Found as per expected |  | Step-1: Click on Add to Cart button of product |  |  | Passed
111 |  |  |  | Verifying product quantity is updated on cart | Quantity should be updated on the cart | Found as per expected |  | Step-1: Click on Add to Cart button of product Step-2: Click on + button to update quantity |  |  | Passed
112 |  |  |  | Verifying the total price is calculated on the cart | Total price of all product should be calculated | Found as per expected |  | Step-1: Click on Add to Cart button of multiple product Step-2: Click on cart |  |  | Passed
113 |  |  |  | Verifying products can be removed from cart | Products can be removed from cart | Found as per expected |  | Step-1: Add some products to cart Step-2: Go to cart Step-3: Click on delete icon of a product to remove from cart |  |  | Passed
114 |  |  |  | Verifying delivery time is showing on the cart | Product estimated delivery time should appear on the cart | Found as per expected |  | Step-1: Add some products to cart Step-2: Go to cart |  |  | Passed
115 |  |  |  | Verifying cart sidebar open/closes smoothly | Smooth openning and closing of the cart | Found as per expected |  | Step-1: Click on cart button Step-2: Click on cross button on the cart sidebar |  |  | Passed
116 |  |  |  | Verifying CONTINUE CHECKOUT button navigates the user to checkout page if logged in | Logged in user will be taken to the checkout page if the button is pressed | Found as per expected |  | Step-1:Log in Step-2: Click on cart button Step-3: Click on CONTINUE CHECKOUT button |  |  | Passed
117 |  |  |  | Verifying if the CONTINUE CHECKOUT button pressed in logged out state the user is asked to log in | The user should be asked to log in to continue with checkout | Found as per expected |  | Step-1:Stay logged out Step-2: Click on cart button Step-3: Click on CONTINUE CHECKOUT button |  |  | Passed
118 |  |  | Track Order | Verifying both phone number and invoice no is required to track order | Both phone number and invocie no should be required to track order | Found as per expected |  | Step-1:Click on track order Step-2:Try to submit without phone/invoice no. |  |  | Passed
119 |  |  |  | Verifying with wrong invoice number | Both right phone number and Invoice No. should be required top track order | Found as per expected | 1732066805, 131410000 | Step-1:Click on track order Step-2:Insert user's phone number and wrong invocie no. |  |  | Passed
120 |  |  |  | Verifying with valid invoice but wrong phone number | Both right phone number and Invoice No. should be required top track order | Found as per expected | 1732066705, INV728502025 | Step-1:Click on track order Step-2:Insert wrong phone number and a valid invocie no. |  |  | Passed
121 |  |  |  | Verifying with both correct phone number and invoice no | Should display order tracking information | Found as per expected | 1732066805, INV728502025 | Step-1:Click on track order Step-2:Insert phone number and a valid invocie no. |  |  | Passed
122 |  |  |  | Verifying payment status is showing in order tracking | Should display payment status on order tracking | Found as per expected | 1732066805, INV728502025 | Step-1:Click on track order Step-2:Insert phone number and a valid invocie no. Step-3:Check payment status |  |  | Passed
123 |  |  |  | Verifying other tracking related information is displayed on order tracking | Should display other necessary tracking related information | Found as per expected | 1732066805, INV728502025 | Step-1:Click on track order Step-2:Insert phone number and a valid invocie no. Step-3:Check tracking info |  |  | Passed
124 | Check Out |  | Cart Items | Verifying all items of the cart are there on the checkout page | All the cart item should be available on the checkout page | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3:View Cart items on checkout page |  |  | Passed
125 |  |  |  | Verifying cart item quantity can be modified on checkout page | All cart item quantity can be modified on the checkout page | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3:Modify cart items |  |  | Passed
126 |  |  |  | Verifying cart item quantity can be removed on checkout page | Any cart item quantity can be removed on the checkout page | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3:Remove cart item |  |  | Passed
127 |  |  |  | Verifying a message is shown when a product is removed from cart | Any removal of item from cart would show a message | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3:Remove cart item |  |  | Passed
128 |  |  |  | Verifying product image,quantity,price is shown in cart items section | Product relavent information should be displayed | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout |  |  | Passed
129 |  |  |  | Verifying when all product is removed from cart items in checkout page user is redirected to home page | When no product is available on cart the user should be navigated to home page from checkout page | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3:Remove all cart item |  |  | Passed
130 |  |  | Delivery Locations | Verifying saved delivery addresses are shown in delivery locations | Saved delivery addresses should be shown in delivery locations | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3: Check delivery locations |  |  | Passed
131 |  |  |  | Verifying default saved address is primarily selected in delivery locations of checkout page | Default saved address should be initially selected in checkout page | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3: Check delivery locations |  |  | Passed
132 |  |  |  | Verifying other saved address can be selected in delivery locations | Users should be able to select in checkout page | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3: select other delivery location |  |  | Passed
133 |  |  |  | Verifying new address can be added to delivery locations if no address/some address is there | Users should be able to select new address on checkout page | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3: Click on Add button on delivery locations |  |  | Passed
134 |  |  | Payment Methods | Verifying Bkash and SSLCOMMERZ is available in online payment | Bkash and SSLCOMMERZ shoiuld be available in online order | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3: Click on online payment |  |  | Passed
135 |  |  |  | Verifying Visa Card,Master Card,American Express, NExus pay is available under swipe | Visa Card,Master Card,American Express, NExus pay should be available under swipe | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3: Click on Swipe |  |  | Passed
136 |  |  |  | Verifying Cash on Delivery option is available | Cash on Delivery option should be available | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3: Click on COD |  |  | Passed
137 |  |  |  | Verifying Online payment options are working and taking to payment gateway | Online payment options should work and take the user to payment gateway once they checkout | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3: Click on Online Payment Step-4:Fill other fields Step-5:Confirm Order |  |  | Passed
138 |  |  |  | Verifying Swipe payment options are working and taking to payment gateway | Swipe options should work and take the user to payment gateway once they checkout | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3: Click on Swipe Step-4:Fill other fields Step-5:Confirm Order |  |  | Passed
139 |  |  |  | Verifying incomplete/cancelled payment is marked | Should notify the user that payment wasn't made | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3: Click on Swipe Step-4:Fill other fields Step-5:Confirm Order |  |  | Passed
140 |  |  |  | Verifying order isn't placed in case of incomplete/cancelled payment | The order shouldn't be placed if the payment procedure isn't complete | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3: Click on Swipe Step-4:Fill other fields Step-5:Confirm Order |  |  | Passed
141 |  |  |  | Verifying order is getting placed in case of successfull payment | The order should be placed if the payment procedure is complete | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3: Click on Swipe Step-4:Fill other fields Step-5:Confirm Order |  |  | Passed
142 |  |  | Delivery Date & Time | Verifying Delivery Date calender is appearing on click | Delivery date calendar should open if the user click on the delivery date | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3:Click on calander icon on delivery date and time |  |  | Passed
143 |  |  |  | Verifying past dates can't be selected as delivery date | Past date shouldn't be allowed to select as delivery date | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3:Click on calander icon on delivery date and time |  |  | Passed
144 |  |  |  | Verifying the day user is order and the next 3 days are only available as delivery date | Total of 4 days should be available as delivery date.Starting from date of order till next 3 day | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3:Click on calander icon on delivery date and time |  |  | Passed
145 |  |  |  | Verifying past time slots can't be selected as delivery time | Past times shouldn't be allowed to select as delivery time | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3:Click on delivery time |  |  | Passed
146 |  |  |  | Verifying other time slots can be selected as delivery time | Available time slots should be able to be selected as delivery time | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3:Click on delivery time |  |  | Passed
147 |  |  | Order Summary | Verifying product total price,vat,coupon discount,other discout,delivery charge and total payable is showing | Product total price,vat,coupon discount,other discout,delivery charge and total payable should be displayed | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3:Check order summary |  |  | Passed
148 |  |  |  | Verifying order summary is updated if cart is modified | As the cart modifies the order summary should adjust as well | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3:Increase/Decrease quantity of product Step-4:Check order summary |  |  | Passed
149 |  |  |  | Verifying clicking on delivery charge loads a modal that shows locationwise delivery charges | Users should be made aware which location cost how much charge | Found as per expected |  | Step-1: Add some product to cart Step-2:Continue Checkout Step-3:Click on delivery charge |  |  | Passed
150 |  |  |  | Verifying orders below 500 taka charges 40 Taka as delivery charge | Orders below 500 taka should charge 40 taka as delivery charge | Found as per expected |  | Step-1: Add some product to cart as total is below 500 Step-2:Continue Checkout Step-3:Click on delivery charge |  |  | Passed
151 |  |  |  | Verifying order equal to 500 Taka or greater and under 1500 Taka cost 20 taka as delivery charge | Orders equal to 500 taka and less then 1500 taka should charge 20 taka as delivery charge | Found as per expected |  | Step-1: Add some product to cart as total is equal or greater than 500 and less than 1500 Step-2:Continue Checkout Step-3:Click on delivery charge |  |  | Passed
152 |  |  |  | Verifying order greater than 1500 Taka cost 0 taka as delivery charge | Order above 1500 taka should cost 0 Taka as delivery charge | Not found as per expected. Order equal to 1500 also charges 0 Taka |  | Step-1: Add some product to cart as total is equal 1500 Step-2:Continue Checkout Step-3:Check Delivery charge | Delivery_charge_error.png |  | Failed
153 |  |  | Additional Note | Verifying textbox available for additional notes | A textbox should be available so that user can provide additional note with order | Found as per expected |  | Step-1: Add some product to cart as total is equal 1500 Step-2:Continue Checkout Step-3:Check additonal note |  |  | Passed
154 |  |  |  | Verifying orders are placing with/without additional notes | User may or may not provide additional note. So both case should be accepted by the forrm | Found as per expected |  | Step-1: Add some product to cart as total is equal 1500 Step-2:Continue Checkout Step-3:Continue with/without additional note |  |  | Passed
155 |  |  | Terms & Conditions | Verifying users can view terms and condition by clicking on terms and conditions | Users should be able to view terms and condition by clicking on terms and condition | Not found as per expected. Terms and condition is colored green but not taking anywhere or showing terms and conditions |  | Step-1: Add some product to cart as total is equal 1500 Step-2:Continue Checkout Step-3:Click on Terms and Conditions | terms&condition.png |  | Failed
156 |  |  |  | Verifying users aren't allowed to continue without accepting terms and condition | Users must accept terms and condition to continue with the order | Found as per expected |  | Step-1: Add some product to cart as total is equal 1500 Step-2:Continue Checkout Step-3:Try to proceed without accepting terms and condition |  |  | Passed
157 | Footer |  | Customer Services | Verifying all MeenaBazar outlets address are given inside Meena Bazar Stores section | All Outlets address with phone number should be given | Found as per expected |  | Step-1:Click on Meena Bazar Stores |  |  | Passed
158 |  |  |  | Verifying Frequently asked questions are answered inside Frequently Asked Question section | Frequently Asked Questions should be answered in this section | Found as per expected |  | Step-1:Click on Frequently Asked Questions |  |  | Passed
159 |  |  |  | Verifying Terms and Condition Page shows all the terms and Conditions | Terms and Conditions should be displayed in Terms and Condition Page | Found as per expected |  | Step-1:Click on Terms and Condition |  |  | Passed
160 |  |  |  | Verifying Privacy policy page showing privacy policy | Privacy Policy in footer should take user to Privacy Policy Page | Found as per expected |  | Step-1:Click on Privacy Policy |  |  | Passed
161 |  |  |  | Verifying Recipe Page showing some recipes | The recipe page should display some recipes | Found as per expected |  | Step-1:Click on Recipes |  |  | Passed
162 |  |  |  | Verifying clicking on each recipe takes the user to detailed recipe page | Each recipe should be displayed in details | Found as per expected |  | Step-1:Click on Recipes Step-2: Click on each recipe cards |  |  | Passed
163 |  |  | About MEENA BAZAR | Verifying About Meena Bazar shows information about meena bazar | About Meena Bazar should take the user to a page that displays information about Meena Bazar | Found as per expected |  | Step-1:Click on About Meena Bazar |  |  | Passed
164 |  |  |  | Verifying Shipping and Delivery link on footer | The page should mention delivery modality,delivery charges and delivery disclaimer | Not found as per expected. Delivery Charges doesn't match with the checkout page |  | Step-1: Click on Shipping and Delivery Step-2:Add product of given range in the cart to match delivery charge Step-3:Check Delivery charge in checkout page | shipping_and_delivery_error.png |  | Failed
165 |  |  |  | Verifying Customer care information is provided in Customer Care page | The customer care available hour,contact and email should be displayed on Customer Care page | Found as per expected |  | Step-1:Click on Customer Care |  |  | Passed
166 |  |  |  | Verifying Careers page | The careers page should show career opportunities at meenabazar if available, otherwise it should let the user know about unavailability of such opportunities | Not found as per expected. Loading an errorpage |  | Step-1:Click on Careers | career_error.png |  | Failed
167 |  |  | Contact Us | Verifying under the Contact us in footer contact details are provided | The address,email and contact number should be provided | Found as per expected |  | Step-1: Check Contact Us |  |  | Passed
168 |  |  | Download App | Verifying google play store app button is redirecting to the app link | Should take the user to the MeenaBazar app on play store | Found as per expected |  | Step-1:Click on Get it on Google Play |  |  | Passed
169 |  |  |  | Verifying app app button is redirecting to the app link | Should take the user to the MeenaBazar app on app store | Found as per expected |  | Step-1:Click on Get it on App Store |  |  | Passed
170 |  |  | Social Handles | Verify Facebook Icon Redirects to the Correct Store Page | Should redirect user to facebook page of Meena Bazar | Found as per expected |  | Step-1:Click on Facebook Icon |  |  | Passed
171 |  |  |  | Verify YouTube Icon Redirects to the Correct Channel | Should redirect user to YouTube Channel of Meena Bazar | Found as per expected |  | Step-1:Click on YouTube Icon |  |  | Passed
172 |  |  |  | Verify Linkden Icon Redirects to the Company Linkden Profile | Should redirect user to Linkden Profile of Meena Bazar | Found as per expected |  | Step-1:Click on Linkden Icon |  |  | Passed
173 |  |  |  | Verify Instagram Icon Redirects to the Correct Store Profile | Should redirect user to Instagram Profile of Meena Bazar | Found as per expected |  | Step-1:Click on Instagram Icon |  |  | Passed
174 |  |  |  | Verifying all the social links are openning on a new tab | Should open a new tab for all the social handles if clicked | Found as per expected |  | Step-1: Click on all the social handles |  |  | Passed
175 |  |  | Browser Compatibility | Verifying various browser compatibility | Should run in different browsers | Found as per expectation | Chrome,Edge,Firefox | Step-1:Open Browser Step-2: Search using the site URL |  |  | Passed
Negative test

## Test Summary Report
Test Case Report | [5 empty] | Result :
Project Name | MeenaBazar
Module Name | Account, Home, Product Categories, Shopping Management, Checkout, Footer | [6 empty] | New Features:- | Testing Scope:-
Feature Name | Login, Personal Info, Wishlist, Dashboard, Saved Address, Order History, Log Out, Featured Product, Special offers, New Arrival, Product Categories, Product Search, Shopping Cart, Track Order, Checkout, Footer |  |  |  |  | Total No. | Status
Test Case Version | 1 |  |  |  |  | 166 | PASS
Written By | Md. Kawsar Hossain |  |  |  |  | 9 | FAIL
Executed By | Md. Kawsar Hossain |  |  |  |  | 0 | Not Executed
Reviewed By | [5 empty] | 0 | Out of Scope
TEST EXECUTION REPORT
Testing Environment : Google Chrome Browser
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 166 | 9 | 0 | 0 | 175
Grand Total | 166 | 9 | 0 | 0 | 175
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting
#SL 01
Issue: OTP resend button pressed, But no OTP received via Email/Mobile Number
Reproducing Steps:
1. Goto the URL https://meenabazaronline.com/
2. Click on the "Sign In" button
3. Enter valid email/mobile and press Continue
4. Wait for the OTP Re-send timer to end and press Re-send
5. Check mail/message for OTP
Env: Production
Module: Login
Priority: P1
Severity: Major
ScreenShot: Resend_button_error.png
Expectation: Should resend an OTP to the email/phone with proper confirmation message. For mobile number
login, display: "OTP is sent to your mobile number." For email login, display: "OTP is sent to your email."
Responsible QA: Md. Kawsar Hossain
Bug Reporting
#SL 02
Issue: Sign-In flow does not reset and lacks back navigation option
Reproducing Steps:
1. Goto the URL https://meenabazaronline.com/
2. Click on the "Sign In" button
3. Enter email/phone and press Continue
4. Close the Sign in Modal
5. Click on the Sign In button again
Env: Production
Module: Login
Priority: P1
Severity: Major
ScreenRecord: Sign_in_reattempts.mp4
Expectation: Closing and reopening the sign-in form should reset the process to the initial step. A Back button should be available to navigate to the previous step and modify the entered credentials
Responsible QA: Md. Kawsar Hossain
Bug Reporting
#SL 03
Issue: Cursor isn't initially on the input field once the sign-in modal opens
Reproducing Steps:
1. Goto the URL https://meenabazaronline.com/
2. Click on the "Sign In" button
Env: Production
Module: Login
Priority: P2
Severity: Minor
ScreenShot: Cursor_error.png
Expectation: The cursor should be on the input field
Responsible QA: Md. Kawsar Hossain
Bug Reporting
#SL 04
Issue: Breadcrumbs not linked to some product categories
Reproducing Steps:
Step-1:Click on categories
Step-2: Click on a "Personal Care/HouseHold
Step-3:Click on a product card
Step-4: Click on the breadcrumb 2nd level
Env: Production
Module: Product Categories
Priority: P2
Severity: Major
ScreenShot: Breadcrumbs_error.png
Expectation: Clicking on any level of the breadcrumbs should navigate to right path
Responsible QA: Md. Kawsar Hossain
Bug Reporting
#SL 05
Issue: Searching with special characters displays all the products
Reproducing Steps:
Step-1: Search with special characters
Env: Production
Module: Shopping Management
Priority: P2
Severity: Minor
ScreenShot: searching_with_special_characters_error.png
Expectation: Searching with speical charater should show no search results
Responsible QA: Md. Kawsar Hossain
Bug Reporting
#SL 06
Issue: Order Amount equal to 1500 is getting free delivery
Reproducing Steps:
Step-1: Add some product to cart as total is equal 1500
Step-2:Continue Checkout
Step-3:Check Delivery charge
Env: Production
Module: Check Out
Priority: P1
Severity: Major
ScreenShot: delivery_charge_error.png
Expectation: Order above 1500 taka should cost 0 taka as delivery charge
Responsible QA: Md. Kawsar Hossain
Bug Reporting
#SL 07
Issue: Clicking on Terms and Condition in Checkout page is not displaying terms and condition
Reproducing Steps:
Step-1: Add some product to cart as total is equal 1500
Step-2:Continue Checkout
Step-3:Check Delivery charge
Env: Production
Module: Check Out
Priority: P2
Severity: Minor
ScreenShot: terms&condition_error.png
Expectation: Terms and Condition should be displayed for the user
Responsible QA: Md. Kawsar Hossain
Bug Reporting
#SL 08
Issue: Delivery Charges given in Shipping and Delivery doesn't match with the actually charged amount
Reproducing Steps:
Step-1: Click on Shipping and Delivery
Step-2:Add product of given range in the cart to match delivery charge
Step-3:Check Delivery charge in checkout page
Env: Production
Module: Footer
Priority: P1
Severity: Major
ScreenShot: Shipping_and_delivery_error.png
Expectation: Delivery charges need to be updated
Responsible QA: Md. Kawsar Hossain
Bug Reporting
#SL 09
Issue: Clicking on Careers is loading an error page
Reproducing Steps:
Step-1: Click on Careers
Env: Production
Module: Footer
Priority: P2
Severity: Minor
ScreenShot: careers_error.png
Expectation: There should be some content in careers page or it should be removed from footer
Responsible QA: Md. Kawsar Hossain

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (172/172)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/172)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (163/172)*100 = 94.8%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (9/172)*100 = 5.2%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/172)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A